## Sheet1
Planning for SQL migration
Pre Migration
Check and fix the orphan users if any for source servers before we start migration for any server
Script out the logins and permissions through RevLogin and SPs
Make sure correct connection strings are maintained in Azure DevOps
Segregate the logins into three categories namely Windows Users, SQL Users and AAD groups
Create the AD groups in advance for the windows users and add them at instance level
Check the Linked Servers configurations and test connectivity at source
Fix Firewall rules before creating and testing Linked Servers on target machines
Fix Firewall rules for the source endpoints on target machines
Script out and create the Linked Server and test the connectivity at the target
Script out and create Triggers
Script out and create Operators
We need to ask Ahmed to give read permissions to SQL MI instance so that it could query the Microsoft Entra IDs (to avoid the "Server Identity could not read the Azure AD Reader Permissions" error)
Post Migration
Launch the Azure Managed Instance Link and perform failover (cutover)
Once failover is done, chedk the status of the database and make sure it is completely available
Copy the permission scripts and start executing
drop the users (don't remove the Sunwing\)
create the users from login (Remove the Sunwing\) and execute the script
execute the roles and permissions script
Give similar permissions to the new AD groups created with Windows users (Svc_accounts) added to it
Enable the jobs associated
** It takes roughly 40 minutes - 1 Hr. to perform the cutover for a single database even for databases like PCS